## May, 2025
Date | Task Aligned | Feedback
2025-05-01 | Holiday | Hoilday
2025-05-02 | design pattern and development structure(www.tasremoval.co.uk) | Started Work around Website Structure & Design Idea
2025-05-03 | Re: ASSIGNMENT CODE: MHA 2361 | Submission Completed
2025-05-04 | Sunday | Sunday
2025-05-05 | Working on the Development of www.tasremoval.co.uk , designs for BollyEntertainment Side | Pages Creations and Ul Designs, Logos and Design submitted
2025-05-06 | www.tasremoval.co.uk Quote panel | Finalize the quotes from shiv sir and started preparing the backend
2025-05-07 | MHA 2709 , VINAY LINGA , NEPTUNE_Loans_Data_analysis | Submission Completed
2025-05-08 | Project Update: Updated Quote Form with Authentication of www.tasremoval.co.uk | Authentication Added to Quote Submission:
2025-05-09 | AJAX Form Handling – Tas Removal | implemented AJAX on the quote form to allow real-time, smooth submissions without reloading the page
2025-05-10 | Project Update:www.tasremoval.co.uk implemented AJAX on the quote form to allow real-time, smooth submissions without reloading the page | All hyperlink references across the WordPress admin (wp-admin) have been streamlined for consistency and accuracy.
2025-05-11 | Sunday | Sunday
2025-05-12 | Homepage Redesign and Functional Enhancements www.tasremoval.co.uk | homepage is now live on the staging environment and ready for review:
2025-05-13 | Quote Page Design and AJAX Form Implementation www.tasremoval.co.uk, MHA 2581 Justification ERD, MHA 2348 Submission of Hirad Loan Data Analysis – Pre-Code Run with File Upload Handling | Submission Completed
2025-05-14 | COMP7060 Data Management – Final Resubmission Submission - MHA 2581 | final resubmission for the COMP7060 Data Management module. In this revised submission, I have thoroughly addressed all feedback and ensured that the project now meets the assignment’s technical and academic criteria.
2025-05-15 | Update on Page Break & Quote Handling – Ahmed Movers UK (https://ahmmedmovers.co.uk/) | Recent enhancements regarding page break and quote handling Solved
2025-05-16 | Project Update – Ahmed Movers UK ¦ User Panel, Login Module & Report Enhancements | I'm currently waiting on the domain a final round of testing.
2025-05-17 | enhancements made to the Admin Panel and Quote Management features | Impletion Completed
2025-05-18 | Sunday | Sunday
2025-05-19 | Update on Contact Page Build and User Setup – Ahmed Movers UK (https://ahmmedmovers.co.uk/) | Admin has complete visibility over inbound queries and the users receive timely feedback, boosting overall service efficiency.
2025-05-20 | Progress Update: Backend Design of Freelancer Task Assignment and Monitoring Tool | update on the progress made today regarding the Freelancer Task Assignment and Monitoring Tool project.
2025-05-21 | WP Employee Activity Tracker – Phase 1 Completed & Phase 2 Analysis(work.cognicierge-solutions.com) | progress of the WP Employee Activity Tracker plugin development.
2025-05-22 | Activity Tracking with JavaScript & REST API (Implemented) | Progress of the WP Employee Activity Tracker plugin development.
2025-05-23 | Phase 3 Development Update – Employee Activity Tracking System | The system logic for inactivity detection, tool whitelisting, and daily session control is being implemented and tested incrementally.
2025-05-24 | Update : Employee Tracker - Dashboard and User Fix | Employee Tracker: https://admin.infizestpublishings.com/ User Login Credentials made Please check the key features including login functionality, employee activity tracking, and data display components.
2025-05-25 | Sunday | Sunday
2025-05-26 | BM9720 - Aravind assignment Submissons - , | Reversed Code and Colab Submitted
2025-05-27 | ASSIGNMENT CODE: MHA 2987 , Website Submisson | Given in wordpress , later chnaged to wix
2025-05-28 | Backend Development: Core Focus Areas in Phase 4 - Crm Development | Database Design & Optimization,
2025-05-29 | Database Design & Optimization (Extended) | Integration testing of AJAX endpoints across different user roles, New Tables Added:
2025-05-30 | Updates on Employee Time Tracker Crm Infizest | Frontend Dashboard Enhancements, Admin Menu Improvements
2025-05-31 | Backend Design Update – Employee Time Tracker | Database & Logging Enhancements, . Reporting System, Monthly Summary Report:, Aggregates working hours, break durations, number of breaks per user. Displays start, break, resume, and end events in chronological order. Useful for performance audits and HR review.
2025-06-01 | Sunday | Sunday
2025-06-02 | Progress Update: Timing Calculations and AJAX | system’s responsiveness and ensuring accurate timing functionality across relevant modules.
2025-06-03 | Domain Renewal for infizestpublishings.com , Backend Update – Infizest Employee Tracker | Update the SSL , cl/cd bashline , Domiain Renwal, Session and Middleware Fixes, Login & Access Handling, Admin Panel Enhancements
2025-06-04 | Backend Update – Infizest Employee Tracker Application (Socket.io & Notifications Implemented) | Session and Middleware Enhancements, Real-Time Notification System
2025-06-05 | Dashboard Update: Accurate Break Time Tracking & Resume Button Added | Accurate Break Time Calculation, New “Resume to Work” Button
2025-06-06 | ASSIGNMENT CODE: VENDOR - 064 ,(Feedback) | Python Coding , Colab Colab Link: https://colab.research.google.com/drive/1TLct1Z9or1D4f0aJHcysLCa03mDv_uo-?usp=sharing
2025-06-07 | Fwd: ASSIGNMENT CODE: VENDOR - 075 | Python Coding, Colab Implemented .Google Colab Link: https://colab.research.google.com/drive/1_nYnYQaeVecYivYB8dfCgpEAmwu5qVeH?usp=sharing Revised File
2025-06-08 | ASSIGNMENT CODE: MHA 3023 - TANMAY CHAUHAN (RISHABH) | submission for MHA 3023_TANMAY CHAUHAN_APSP_Assignment_G1_Oct24_Transforming_Algorithm_Into_Python Google Colab Notebook: https://colab.research.google.com/drive/1Vk88wnCcgQXoFYqMFUKbN4cZxRu7QfLM?usp=sharing
2025-06-09 | Dashboard Update: Accurate Break Time Tracking | Accurate Break Time Calculation, New “Resume to Work” Button, Instant UI Feedback
2025-06-10 | Updates on Infizest Employee Tracker – Employee User List & Multer Integratio | Employee User List with Task Activity Tracking, Multer and Server-Side Installations
2025-06-11 | Task Feed Panel for Admins and Employees (Infizest Employee Tracker) | implemented a new Feed Panel module in the Infizest Employee Tracker. This panel enables admins to post work feeds with task details including title, description, deadline, and attachments. All employees can view these tasks in real time and use the "Pick" button to express interest. (Backend Update)
2025-06-12 | Casual Leave | Casual Leave
2025-06-13 | New Feed Panel Module Implementation – Infizest Employee Tracker | This module is designed to promote transparency, collaboration, and real-time task tracking within the team. You can review the current implementation on our development environment via the following link: Server & Site (VPS): https://l3q93v4q-3000.inc1.devtunnels.ms/
2025-06-14